## Effort Breakdown
Issue # | Summary of Tasks | Estimate (hours) | Coding Effort (hours) | Non-Coding Effort (hours) | Estimator | Implementors
1 | Create Event Search & Sign Up Page Mockup for presentation | 1 | 1 | 0 | Jiayi Liu | Sakura Takahashi
2 | Create Sign In Mockup Page | 1 | 0 | 1 | Sakura Takahashi | Kacy Kuniyoshi
3 | Design and implement database schema | 3 | 2 | 4 | Jordan Wong | Jordan Wong
4 | Create UserHome/Contact/About Us Page Mockup | 1 | 0 | 1 | Kacy Kuniyoshi | Alicia Luckman
5 | Deploy System to Vercel | 1 | 0 | 2 | Kacy Kuniyoshi | Jiayi Liu
6 | Create Landing Page Mockup | 2 | 3 | 0 | Kacy Kuniyoshi | Sakura Takahashi, Jordan Wong
7 | Create Sign In/ SIgn Up page for Warriorhub Repo | 1 | 0 | 1 | Kacy Kuniyoshi | Jiayi Liu
8 | Create and Populate Milestone 2 Project Page | 1 | 1 | 0 | Jiayi Liu | Sakura Takahashi
9 | Create Landing Page/Organizer Home Page Mockup | 1.5 | 0 | 1 | Sakura Takahashi | Kacy Kuniyoshi
10 | Deploy Nextjs-template to Warriorhub Respitory | 3 | 0 | 2 | Kacy Kuniyoshi | Jiayi Liu
11 | Update Project Home Page (Update github.io page) M1 | 4 | 3 | 1 | Kacy Kuniyoshi | Sakura Takahashi, Jordan Wong
12 | Complete Vercel Deployment Documentation | 0.5 | 0 | 0.5 | Sakura Takahashi | Jiayi Liu
13 | Create Admin Home Page Mockup for presentation | 1 | 0 | 2 | Sakura Takahashi | Kacy Kuniyoshi
14 | Create Event Search Page (html, vscode, etc.) | 3 | 3 | 1 | Sakura Takahashi | Kacy Kuniyoshi
15 | Implement Role‑Based Home Pages | 1.5 | 5 | 1 | Alicia Luckman | Alicia Luckman & Kacy Kuniyoshi
16 | Update Packages to the Latest Version Specified In package.json | 0.5 | 0.2 | 0.1 | Jordan Wong | Jordan Wong
17 | Fix User Home Page Mockup | 1 | 1 | 0 | Jiayi Liu | Sakura Takahashi
18 | Implement Sign Up Functionality | 3 | 2 | 1 | Kacy Kuniyoshi | Sakura Takahashi, Jordan Wong
19 | Create Admin Home Page | 2 | 1 | 0.5 | Sakura Takahashi | Sakura Takahashi
20 | Create Event Functionality | 2 | 0.5 | 0.5 | Kacy Kuniyoshi | Jordan Wong, Jiayi Liu
21 | Update Project Home Page (Update GitHub.io Page) M2 | 3 | 2.5 | 1 | Sakura Takahashi | Sakura Takahashi
24 | Populate User Home Page and Landing Page with Events | 2 | 0.5 | 0 | Kacy Kuniyoshi | Jiayi Liu
25 | Build Events Detail Page | 2 | 0.5 | 0 | Kacy Kuniyoshi | Jiayi Liu
27 | Implement Update & Delete Feature for Admins and Organizers | 3 | 3.2 | 1.1 | Kacy Kuniyoshi | Kacy Kuniyoshi
29 | Create Interested Feature Functionality | 3 | 2 | 0 | Kacy Kuniyoshi | Sakura Takahashi
30 | Create Milestone 3 Project Page | 0.5 | 0 | 0.4 | Kacy Kuniyoshi | Alicia Luckman
34 | Add Event Categories To Schema | 1 | 0.75 | 1 | Jiayi Liu | Sakura Takahashi, Jordan Wong
36 | Create Organizer Home Page | 3 | 4 | 0 | Sakura Takahashi | Alicia Luckman & Kacy Kuniyoshi
37 | Create Event Details Cards | 2 | 1 | 0.5 | Kacy Kuniyoshi | Kacy Kuniyoshi
38 | Set up GitHub Actions to manage migrations | 2 | 0.6 | 1.7 | Sakura Takahashi | Jordan Wong
39 | Create My Events Page | 1.5 | 1 | 0 | Sakura Takahashi | Sakura Takahashi
40 | Create Contact Us / Help Page | 1.5 | 1 | 0 | Sakura Takahashi | Sakura Takahashi
41 | Populate the effort estimation Google spreadsheet | 1 | 0 | 4 | Kacy Kuniyoshi | Alicia Luckman, Sakura Takahashi, Kacy Kuniyoshi
42 | Add Effort Estimation Fields to Project Milestone | 0.5 | 0 | 0.1 | Kacy Kuniyoshi | Kacy Kuniyoshi & Jordan Wong
43 | Add Comments To Each Issue About Estimated Effort | 0.5 | 0 | 0.5 | Sakura Takahashi | Sakura Takahashi, Kacy Kuniyoshi, Jiayi Liu, Jordan Wong, Alicia Luckman
44 | Create Role System For User, Organizer, & Admin | 2 | 2 | 0.5 | Sakura Takahashi | Sakura Takahashi
46 | Create dbactions Logic For User/Organizer/Admin Home Page | 1 | 0.75 | 0 | Sakura Takahashi | Sakura Takahashi
47 | Create Api Access to Call Each Page to their Respective Role Type | 2 | 2.2 | 0.4 | Kacy Kuniyoshi | Kacy Kuniyoshi
48 | Implement Add Page | 2 | 1.5 | 0 | Kacy Kuniyoshi | Jiayi Liu
51 | Implement the Functioning Calendar Page | 2 | 2 | 0 | Sakura Takahashi | Jiayi Liu
55 | Implement Playwright into WarriorHub | 2 | 1.2 | 3.2 | Sakura Takahashi | Kacy Kuniyoshi
56 | Update the Seed Script to Use the Provided Category Data | 0.4 | 0.05 | 0.05 | Jordan Wong | Jordan Wong
58 | Generate Migration For GitHub Database | 1 | 0.75 | 0 | Jordan Wong | Sakura Takahashi
59 | Load Search Page Events from Database | 3 | 3 | 0.7 | Kacy Kuniyoshi | Kacy Kuniyoshi
60 | Implement Event Search | 2 | 2.8 | 0.2 | Kacy Kuniyoshi | Kacy Kuniyoshi
62 | Use Another Table (Data Model) for Event Category | 3.5 | 1.6 | 2.4 | Jordan Wong | Jordan Wong
63 | Admin List Events Page Front End | 3 | 2 | 1.4 | Kacy Kuniyoshi | Kacy Kuniyoshi
64 | Show Current Date When Returning to Calendar Page | 1 | 0.2 | 0 | Sakura Takahashi | Jiayi Liu
65 | Fix User Homepage | 2 | 2 | 0 | Kacy Kuniyoshi | Jiayi Liu
66 | Fix My Events Page | 1.5 | 0.75 | 0 | Sakura Takahashi | Sakura Takahashi, Jiayi Liu
67 | Fix My Events Page Functionality (For Organizers) | 1.5 | 3 | 2 | Sakura Takahashi | Jiayi Liu
68 | Fix MyEvents Routing Page Logic | 1 | 1 | 0 | Sakura Takahashi | Sakura Takahashi
69 | Create Archived Events Data Model [skipped due to time constraints] | 2 | N/A | N/A | Sakura Takahashi | Jordan Wong
70 | Fix M3 Project Page | 0.5 | 0 | 0.5 | Sakura Takahashi | Sakura Takahashi
71 | Fix The Images URL | 1.5 | 0.5 | 0 | Sakura Takahashi | Jiayi Liu
72 | Fix Event Details Organization Name | 1.5 | 1.75 | 0 | Sakura Takahashi | Sakura Takahashi
73 | Edit dbActions/authOptions/routers for Organizers | 1 | 1 | 0 | Sakura Takahashi | Jiayi Liu
74 | Find 5 community members | 1 | 0 | 0.3 | Sakura Takahashi | Alicia Luckman, Kacy Kuniyoshi, Sakura Takahashi
75 | Update community feedback on GitHub.io | 1 | 0 | 1 | Sakura Takahashi | Alicia Luckman
76 | Create admin home page playwright tests | 1 | 0 | 2.3 | Sakura Takahashi | Kacy Kuniyoshi
77 | Fix the list events page to be static for the admin | 0.75 | 0.75 | 0 | Sakura Takahashi | Sakura Takahashi
78 | Add deployment link to READ.me in the github.io repo and warriorhub repo | 0.083 | 0 | 0.083 | Sakura Takahashi | Sakura Takahashi
79 | Add more playwright test cases | 2 | 0 | 1.9 | Sakura Takahashi | Kacy Kuniyoshi
80 | Fix Edit User form Routing | 1 | 1 | 0 | Kacy Kuniyoshi | Jiayi Liu
81 | Update frontend code to use CategoriesNew | 1.75 | 1.75 | 0 | Jordan Wong | Sakura Takahashi
82 | Populate real event data | 3 | 3 | 0 | Sakura Takahashi | Sakura Takahashi, Jiayi Liu
83 | Update the Github.io page parts 1 | 2 | 0 | 2 | Kacy Kuniyoshi | Alicia Luckman, Sakura Takahashi
84 | Update the Github.io page (other parts) | 1 | 0 | 1.5 | Kacy Kuniyoshi | Alicia Luckman, Sakura Takahashi
85 | Make Featured events populate with current events and render organization name | 1.75 | 1 | 0.25 | Sakura Takahashi | Sakura Takahashi
86 | Fix Event Time | 5 | 5.5 | 2.5 | Jiayi Liu | Jordan Wong, Jiayi Liu
87 | Edit event page access control | 1.5 | 1.75 | 0 | Jordan Wong | Sakura Takahashi
89 | Fix Admin Access and Search Event to display events in ascending order | 1.5 | 1.5 | 0 | Sakura Takahashi | Sakura Takahashi
90 | Fix Calender page view and organize admin account list page | 1 | 1 | 0 | Sakura Takahashi | Sakura Takahashi
91 | Fix Organizer Home page, Interested delete, and edit functionality | 1 | 2 | 0 | Sakura Takahashi | Sakura Takahashi
92 | Fix Playwright Tests | 2 | 0.2 | 3.4 | Kacy Kuniyoshi | Kacy Kuniyoshi
106 | Edit Event QoL | 1 | 0.6 | 1 | Jordan Wong | Jordan Wong

## Team Summary
Team Member | Software Development Experience (months) | How was coding effort tracked | How was non-coding effort tracked?
Sakura Takahashi | 3 | PomoDoro Technique | PomoDoro Technique
Kacy Kuniyoshi | 3 | WakaTime | Toggl
Jiayi Liu | 3 | Start/Stop Timer | Start/Stop Timer
Jordan Wong | 6 | Clock, GitHub timestamps | Clock, GitHub timestamps
Alicia Luck | 3 | GitHub | N/A